## Sheet1
One Step GPS
ENTERPRISE-GRADE FLEET TRACKING WITHOUT THE BS — $13.95/MO, NO CONTRACTS
onestepgps.com • 888-919-7536
Fleet GPS Migration Checklist
👉 For fleets within 12 months of contract renewal
👉 This checklist is meant to help you plan, sequence, and de-risk a fleet GPS transition.
👉 Not every item will apply to every fleet — use it as a guide, not a mandate.
| Phase 1: Clarify why you’re switching (9–12 months out) | Notes
FALSE | Document the primary reasons you’re considering a switch
(e.g., support issues, reliability, pricing, contract friction)
FALSE | Identify what must be better with the next provider
(non-negotiables vs nice-to-haves)
FALSE | Note which problems you’re willing to tolerate vs fix immediately
FALSE | Align internally on success criteria
(operations, finance, safety, compliance)
FALSE | Assign a single owner for the migration process
Phase 2: Contract awareness & timing (9–12 months out)
FALSE | Locate your current contract and renewal terms
FALSE | Identify:
• Contract end date
• Auto-renew window
• Required notice period
• Early termination fees
FALSE | Set calendar reminders for:
• Auto-renew deadline
• Cancellation notice deadline
• Internal decision milestones
FALSE | Confirm whether any assets or subscriptions are seasonal or inactive
Phase 3: Research & shortlisting (6–9 months out)
FALSE | Create an initial shortlist of viable providers—we created this tool to help you with that:
onestepgps.com/compare/fleet-tracking-providers
FALSE | Eliminate providers that clearly don’t meet your non-negotiables
FALSE | Compare:
• Contract structure
• Pricing transparency
• Support availability
• Hardware options
• Data access policies
FALSE | Review third-party feedback for recurring issues, not one-off complaints
Phase 4: Evaluation & testing (4–6 months out)
FALSE | Schedule demos focused on your workflows, not generic features
FALSE | Test with a small subset of vehicles (2–10 where possible)
FALSE | Validate:
• Location accuracy
• Refresh rate
• Alert behavior
• Reporting usability
• Mobile vs desktop experience
FALSE | Interact with support during testing to evaluate responsiveness
FALSE | Document gaps or concerns surfaced during testing
Phase 5: Cancellation preparation (3–4 months out)
FALSE | Confirm cancellation process and required notice format
FALSE | Prepare written cancellation notice in advance
FALSE | Verify where and how cancellation must be submitted
FALSE | Confirm receipt once submitted
FALSE | Save documentation for your records
Phase 6: Migration asset inventory (2–3 months out)
FALSE | Compile a current list of:
• Vehicles and assets
• Driver records
• Groups and naming conventions
FALSE | Inventory:
• Geofences
• Alerts
• Standard reports
• Custom reports or dashboards
FALSE | Identify which items:
• Can be recreated easily
• Require manual setup
• Will not transfer between systems
Phase 7: Data preservation planning (2–3 months out)
FALSE | Identify data you may want to retain after cancellation, such as:
• Mileage summaries
• Utilization reports
• Compliance documentation
• Incident history
FALSE | Export or archive:
• Reports used for audits or disputes
• Historical summaries you may reference later
FALSE | Note data that typically does not migrate:
• Vendor-specific scores
• AI-modeled insights
• Raw high-frequency data
• Video archives
Phase 8: Hardware & install planning (1–2 months out)
FALSE | Confirm device types needed (plug-in, hardwired, battery, camera, etc.)
FALSE | Plan installation approach:
• In-house vs third-party
• Staggered vs all-at-once
FALSE | Schedule installs to minimize downtime
FALSE | Decide whether old hardware will be:
• Removed
• Deactivated
• Returned later
Phase 9: Transition & go-live (contract end)
FALSE | Activate new devices
FALSE | Confirm all vehicles are reporting correctly
FALSE | Validate:
• Alerts
• Geofences
• Reports
• User access
FALSE | Deactivate old system access as appropriate
Phase 10: Day-one enablement (first week)
FALSE | Train users on essential workflows only
FALSE | Provide quick-reference guides or contacts for support
FALSE | Set expectations for how data will be used
FALSE | Gather early feedback from dispatchers, managers, and drivers
Phase 11: Stabilization & optimization (first 1–3 months)
FALSE | Identify and address migration gaps
FALSE | Rebuild advanced reports or workflows
FALSE | Fine-tune alerts and thresholds
FALSE | Review early performance vs expectations
FALSE | Document lessons learned for future transitions
Final note
Most fleet GPS migrations succeed not because they are fast, but because they are planned.
If you’re within a year of renewal, starting early gives you:
• Leverage
• Optionality
• And a smoother transition
Use this checklist as a working document, not a pressure tool.